## Slide 1: Software Engineering (CS34102)
Department of Computer Science and Engineering
MNNIT, Allahabad
Software Project Planning
Course Instructor: Akanksha Gaur
Course Co-ordinator:
Prof. (Dr.) D.S. Kushwaha

## Slide 2: Contents
Software Project Planning
Size Estimation
Growth of Lines of Code
Function Point
Function Point Analysis
Functional Unit
Functional Unit Categories
Special Features
Counting Function Points
Calculation of UFP
Computing Function Points
Number of factors considered ( Fi )
Metrics
Relative Cost of Software Phases
Cost to Detect and Fix Faults

## Slide 3: Software Project Planning
After the finalization of SRS, estimate
size
cost
development time
Customer may like to know the cost and development time even prior to finalization of the SRS.
3

## Slide 4: Software Project Planning
Scope of work to be done
The risk to be incurred
The resources required
The task to be accomplished
The cost to be expended
The schedule to be followed
4
Notes: In order to conduct a successful software project, we must understand:

## Slide 5: Software Project Planning
Software planning begins before technical work starts, continues as the software evolves from concept to reality, and culminates only when the software is retired.
5
Project Scheduling
Size Estimation
Cost Estimation
Resource Requirements
Development Time
Notes: Activities during Software Project Planning

## Slide 6: Size Estimation
1. | int. sort (int x[ ], int n)
2. | {
3. | int i, j, save, im1;
4. | /*This function sorts array x in ascending order */
5. | If (n<2) return 1;
6. | for (i=2; i<=n; i++)
7. | {
8. | im1=i-1;
9. | for (j=1; j<=im; j++)
10. | if (x[i] < x[j])
11. | {
12. | Save = x[i];
13. | x[i] = x[j];
14. | x[j] = save;
15. | }
16. | }
17. | return 0;
18. | }
Lines of Code (LOC)
If LOC is simply a count of the number of lines then figure shown below contains 18 LOC .
When comments and blank lines are ignored, the program in figure 2 shown below contains 17 LOC.
Function for sorting an array
6

## Slide 7: Growth of Lines of Code
0
500,000
1,000,000
1,500,000
2,000,000
2,500,000
Jan 1993
Jun 1994
Oct 1995
Mar 1997
Jul 1998
Dec 1999
Apr 2001
Total LOC
Total LOC ("wc -l") -- development releases
Total LOC ("wc -l") -- stable releases
Total LOC uncommented -- development releases Total LOC uncommented -- stable releases
7

## Slide 8: Software Project Planning
If the main interest is the size of the program for specific functionality, it may be reasonable to include executable statements.
Executable statements: lines 5-17 leading to a count of 13.
The differences in the counts are 18 to 17 to 13.
One can easily see the potential for major discrepancies for large programs with many comments or programs written in language that allow a large number of descriptive but non-executable statement.
8

## Slide 9: Conte’s definition of lines of code
“A line of code is any line of program text that is not a comment or blank line, regardless of the number of statements or fragments of statements on the line. This specifically includes all lines containing program header, declaration, and executable and non-executable statements”.
This is the predominant definition for lines of code used by researchers. By this definition, figure shown earlier has 17 LOC.
9

## Slide 10: Function Count
Alan Albrecht while working for IBM, recognized the problem in size measurement in the 1970s, and developed a technique (which he called Function Point Analysis), which appeared to be a solution to the size measurement problem.
10

## Slide 11: Albrecht’s Function Point Analysis
The principle of Albrecht’s function point analysis (FPA) is that a system is decomposed into functional units.
Inputs: information entering the system
Outputs: information leaving the system
Enquiries: requests for instant access to information
Internal logical files: information held within the system
External interface files: information held by other system that is used by the system being analyzed.
11

## Slide 12: FPA Functional Units
User
ILF: Internal logical files EIF: External interfaces
FPAs functional units System
12
User
EIF
Application
ILF
System
User
Inquiries
Input
Output

## Slide 13: Categories of Functional Units
The five functional units are divided in two categories:
(i) Data function types
Internal Logical Files (ILF): A user identifiable group of logical related data or control information maintained within the system.
External Interface files (EIF): A user identifiable group of logically related data or control information referenced by the system, but maintained within another system. This means that EIF counted for one system, may be an ILF in another system.
13

## Slide 14: Categories of Functional Units
Transactional function types
  External Input (EI): An EI processes data or control information that comes from outside the system. The EI is an elementary process, which is the smallest unit of activity that is meaningful to the end user in the business.
  External Output (EO): An EO is an elementary process that generate data or control information to be sent outside the system.
  External Inquiry (EQ): An EQ is an elementary process that is made up to an input-output combination that results in data retrieval.
14

## Slide 15: Special Features
Function point approach is independent of the language, tools, or methodologies used for implementation; i.e. they do not take into consideration programming languages, data base management systems, processing hardware or any other data base technology.
Function points can be estimated from requirement specification or design specification, thus making it possible to estimate development efforts in early phases of development.
15

## Slide 16: Special Features
Function points are directly linked to the statement of requirements; any change of requirements can easily be followed by a re-estimate.
Function points are based on the system user’s external view of the system, non-technical users of the software system have a better understanding of what function points are measuring.
16

## Slide 17: Counting Function Points
Functional Units | Weighting factors |  | 
 | Low | Average | High
External Inputs (EI) | 3 | 4 | 6
External Output (EO) | 4 | 5 | 7
External Inquiries (EQ) | 3 | 4 | 6
External logical files (ILF) | 7 | 10 | 15
External Interface files (EIF) | 5 | 7 | 10
Functional units with weighting factors
17

## Slide 18
18
UFP Calculation Table
The weighting factors are identified for all functional units and multiplied with the functional units accordingly.
The procedure for the calculation of Unadjusted Function Point (UFP) is given in table shown above.

## Slide 19: Calculation of UFP
5 3
UFP  ∑∑ Zij wij
i1 J 1
Where i indicate the row and j indicates the column of Table 1
Wij : It is the entry of the ith row and jth column of the table 1
Zij : It is the count of the number of functional units of Type i that have been classified as having the complexity corresponding to column j.
19

## Slide 20: Calculation of UFP
Organizations that use function point methods develop a criterion for determining whether a particular entry is Low, Average or High. Nonetheless, the determination of complexity is somewhat subjective.
FP = UFP * CAF
Where CAF is complexity adjustment factor and is equal to [0.65 + 0.01 x ΣFi].
Fi (i=1 to 14) is the degree of influence and are based on responses to questions noted in table 3.
20

## Slide 21: Computing Function Points
Rate each factor on a scale of 0 to 5.
0 1 2 3 4 5
No Influence
Average
Essential
Incidental Moderate Significant
21

## Slide 22: Number of factors considered ( Fi )
Does the system require reliable backup and recovery ?
Is data communication required ?
Are there distributed processing functions ?
Is performance critical ?
Will the system run in an existing heavily utilized operational environment ?
Does the system require on line data entry ?
Does the on line data entry require the input transaction to be built over multiple screens or operations ?
Are the master files updated on line ?
Is the inputs, outputs, files, or inquiries complex ?
Is the internal processing complex ?
Is the code designed to be reusable ?
Are conversion and installation included in the design ?
Is the system designed for multiple installations in different organizations ?
Is the application designed to facilitate change and ease of use by the user ?
22

## Slide 23: Metrics
Productivity Quality | = = | FP / persons-months Defects / FP
Cost | = | Rupees / FP
Documentation | = | Pages of documentation per FP
These metrics are controversial and are not universally acceptable. There are standards issued by the International Functions Point User Group (IFPUG, covering the Albrecht method) and the United Kingdom Function Point User Group (UFPGU, covering the MK11 method). An ISO standard for function point method is also being developed.
23

## Slide 24: Example
Number of user inputs
Number of user outputs
Number of user enquiries
Number of user files
Number of external interfaces= 04
= 50
= 40
= 35
= 06
Assume all complexity adjustment factors and weighting factors are average. Compute the function points for the project.
24
Consider a project with the following functional units:

## Slide 25: Solution
We know
5 3
UFP  ∑∑ Zij wij
i1 J 1
UFP = 50 x 4 + 40 x 5 + 35 x 4 + 6 x 10 + 4 x 7
= 200 + 200 + 140 + 60 + 28 = 628
CAF = (0.65 + 0.01 ΣFi)
= (0.65 + 0.01 (14 x 3)) = 0.65 + 0.42 = 1.07 FP = UFP x CAF
= 628 x 1.07 = 672
25

## Slide 26: Example
An application has the following:
10 Low external inputs, 12 high external outputs, 20 low internal logical files, 15 high external interface files, 12 average external inquiries, and a value of complexity adjustment factor of 1.10.
What are the unadjusted and adjusted function point counts ?
26

## Slide 27: Solution
Unadjusted function point counts may be calculated using as:
5 3
UFP  ∑∑ Zij wij
i1 J 1
= 10 x 3 + 12 x 7 + 20 x 7 + 15 + 10 + 12 x 4
= 30 + 84 +140 + 150 + 48
= 452
  FP = UFP x CAF
  = 452 x 1.10 = 497.2.
27

## Slide 28: Example
Consider a project with the following parameters.
External Inputs:
  10 with low complexity (b)15 with average complexity
(c) 17 with high complexity
External Outputs:
  6 with low complexity (b)13 with high complexity
External Inquiries:
  3 with low complexity
  4 with average complexity
  2 high complexity
28

## Slide 29
Internal logical files:
  2 with average complexity
  1 with high complexity
External Interface files:
  9 with low complexity
In addition to above, system requires
Significant data communication
Performance is very critical
Designed code may be moderately reusable
System is not designed for multiple installation in different organizations.
Other complexity adjustment factors are treated as average. Compute the function points for the project.
29

## Slide 30
Functional Units | Count Complexity Complexity Totals |  |  |  |  | Functional Unit Totals
External Inputs | 10 15 | Low x 3 Average x 4 | = = | 30 60 |  | 
(EIs) | 17 | High x 6 | = | 102 | 192 | 
External Outputs (EOs) | 6 0 13 | Low x 4 Average x 5 High x 7 | = = = | 24 0 91 | 115 | 
External Inquiries (EQs) | 3 4 2 | Low x 3 Average x 4 High x 6 | = = = | 9 16 12 | 37 | 
External logical | 0 2 | Low x 7 Average x 10 | = = | 0 20 |  | 
Files (ILFs) | 1 High x 15 = |  |  | 15 | 35 | 
External Interface Files (EIFs) | 9 0 0 | Low x 5 Average x 7 High x 10 | = = = | 45 0 0 | 45 | 
 | Total Unadjusted Function Point Count |  |  |  | 424 | 
Solution: Unadjusted function points may be counted

## Slide 31
14
∑ Fi  3+4+3+5+3+3+3+3+3+3+2+3+0+3=41
i1
CAF = (0.65 + 0.01 x ΣFi)
= (0.65 + 0.01 x 41)
= 1.06
FP = UFP x CAF
= 424 x 1.06
= 449.44
Hence FP = 449
31

## Slide 32: Relative Cost of Software Phases
32

## Slide 33: Cost to Detect and Fix Faults
200
180
160
140
120
100
80
60
40
20
0
Req
Des
Int
Cost
Relative Cost to detect and correct fault
33

## Slide 34: References
Software Engineering – A Practitioner’s Approach, by Pressman R.S. and Ince D
Software Engineering by Sommerville
Software Engineering Volume 1 and Volume 2 by Thayer and Christiansen
Software Engineering by KK Aggarwal and Yogesh Singh